## Analysis - Table
Issue | % | Count | Label | Percentage | Count
Operator | 66.4% | 83 | Deviation | 5.344% | 7
Tooling | 1.6% | 2 | Rework | 72.52% | 95
Engineering | 11.2% | 14 | Scrap | 22.14% | 29
Incorrect Time | 0.8% | 1 | Total |  | 131
Programming | 3.2% | 4
Long Setup | 0% | 0
Extra Parts | 2.4% | 3
Surface Finish | 0% | 0
Paint - Prep | 10.4% | 13
Supplier | 1.6% | 2
Routing | 0.8% | 1
Shipped Incomplete | 1.6% | 2
125

## Data
NCR# | Date | Label | Issue | Work Order | NCR Parts | Description | Found In | Charge To | Responsible Party | Correction | Prevention | Time Spent | Cost (Labour) | Cost (Material) | Total Cost | Date Closed | Name
1 | 2021-12-23 | Rework | Operator | 17427-4 |  | Reducer was installed incorrectly | Customer | Welding |  |  | Rethread using die
2 | 2022-01-26 | Rework | Supplier | 17477-1 |  | Door finish was not to satisfaction. Zinc spray was applied on an area more than 1 sq.in | Customer | Supplier |  | Ensure mil thickness is met and finish is uniform | Armour re-galvanized the doors
3 | 2022-02-09 | Rework | Operator |  |  | Doors had couplers welded incorrectly. Wrong end of the coupler was welded to the door | Customer | Welding |  | Coupler end with the spacing needs to be welded to door | Remake x7 doors and retap doors with wrong fitting
4 | 2022-02-15 | Rework | Operator | 17518-1 |  | Backpans studs out of location. backpans were already shipped and the welder had no way to check if the studs were installed correctly | Assembly | Welding | Mark | Make a backpan jig | Made backpan jig to correct locations of studs
5 | 2022-02-16 | Scrap | Operator | 17521-2 |  | 0001-0574 louvers punched inside out. Drawing was not clear. Note for forming to be added by engineers | Welding | Punch |  | Drawing needs to have clear notes | Recut part
6 | 2022-03-02 | Scrap | Operator | 17558-1 |  | Wrong OD Tube used for Axle cover. Florin did not measure the tube and used a 7/8 OD instead of 1 OD. Scrapped 8 bolts | Assembly | Laser | Florin | Check drawing material properties | Recut part using correct tubing
7 | 2022-03-02 | Rework | Engineering | 17559-1 |  | 3/4 Carriage bolt didnt protrude out from nut. Customer drawing incorrectly showed that bolt was long enough for proper bolt stickout | Assembly | Engineering |  | Prototype- Sanitize customer drawings | Ordered longer 1" carriage bolt
8 | 2022-03-03 | Scrap | Operator | 17600-17 |  | Formed incorrectly. In training | Brake | Brake | Mike
9 | 2022-03-08 | Scrap | Engineering | 17594-2 |  | ISM dwg dimension not marked. Brian assumes dimesions are to outside unless specified. Currect rev didnt specify that this was an ISM | Brake | Engineering |  | Inside dimensions to be marked as such | Recut part
10 | 2022-03-15 | Rework | Operator | 17558-1 |  | x2 yellow bodies and x1 blue gauge cutout repaint. The welds were to be ground and the unit pad sanded for an even finish. Heavy grind marks were not apparent until unit was painted | Paint | Paint |  | Grind marks and grit | Need to go easy on grinding the welds
11 | 2022-03-15 | Rework | Paint - Prep | 17558-1 |  | x2 yellow bodies. | Paint | Paint |  | Grind marks and grit
12 | 2022-03-15 | Rework | Operator | 17570-3 |  | Parts were cut 1/8" too long. Flat parts were initially cut wrong. Possible fix with jig was done wrong (jig picked off wrong end). Made a jig and used chopsaw to cut to length | Brake | Cutting | Balwinder | Parts were not inspected against drawing | Use chopsaw to cut extra length for 174 parts
13 | 2022-03-16 | Rework | Operator | 17625 |  | Missing pem. 1 small pem was missed | Customer | Assembly | Siew | Check part to drawing | Customer shipped part and we had to fix and reship
14 | 2022-03-21 | Rework | Engineering | 17594-2 |  | Handle was too wide. Drawing error during design and handle was wider than intended. Customer rejected possible fix. Need to recut handle and reweld | Sales | Engineering | Junfeng | Check customer part | Cut, grind sand and reweld correct handles
15 | 2022-03-21 | Deviation | Operator | 17601-1 |  | Gland plate formed inside out. Gland plate holes are not symmetric and drawing was missing "easily formed backwards". Mistake was not caught until assembly. No rework needed but could have been an issue if customer was specific | Assembly | Brake | Brian | Drawing did not have "easily formed backwards" | Check part to drawing
16 | 2022-03-22 | Rework | Operator |  |  | Missing pems after body was welded. The missing pems were not caught by Siew or Ian. Ian noticed it after the body was welded | Welding | Assembly | Siew | Ensure that work was done on parts | Cut the bottom of body, pem missing studs and reweld
17 | 2022-03-24 | Rework | Operator | 17616-1 |  | Took 4 runs to complete painting the order | Paint/ Assembly | Paint |  | QC needs to be improved. Issues with Grit
18 | 2022-03-25 | Rework | Operator | 17658-3 |  | Grind marks on brake lines. Pad sanding the brake lines took long. Dan and Hussien decided to grind before sanding, which left marks that were very visible after paint. But we repainted 5 times to get it right | Paint | Paint | Hussein/ Dan | New employees should be provided adequate information and oversight when doing a job | Sanding the grind marks away
19 | 2022-04-22 | Rework | Operator | 17685-1 |  | Welds were not ground proper. Might need to refresh shop standards | Paint | Welding | Dilshad | Incomplete grinding | Grinding flush
20 | 2022-04-22 | Rework | Surface Imperfection | 17676-5 |  | Brake marks on door. Paint and brake did not notice brake marks until they were painted | Paint | Brake | Brian | Check for brake marks before paint | Pad sand the parts to get rid of brake marks
21 | 2022-04-25 | Rework | Paint - Prep | 17676-5 |  | Pad sand marks and chemical residue. Pad sanding was not feathered out which made the marks very apparent on the door. Clean parts thoroughy before painted | Paint | Paint | Dan | Ensure pad sand is evened out on the part and clean the parts thoroughly before paint | Resand the parts, clean thoroughly
22 | 2022-04-25 | Scrap | Operator | 17668-2 |  | Part slipped when being bent. One edge of the body was formed wrong. had to recut and reform. | Brake | Brake | Brian
23 | 2022-05-16 | Rework | Paint - Prep | All 17540 WO |  | Speckled finish on black paint. The box of black paint they use was a year old and had some contamination. After painting, there were white specks in black paint which is not the required finish | Paint | Paint |  | Check that theres no contamination during paint/ before oven | Repaint with a new box
24 | 2022-05-16 | Rework | Engineering | All 17540 WO |  | Drawing issues - prototype. Prototypes needed to be reworked, some of them had to repainted | Assembly | Engineering |  | Prototype- Issues are expected | Fix as per mfg direction and eng approval
25 | 2022-05-16 | Rework | Paint - Prep | 17703-1 |  | Grit on top. | Assembly | Paint
26 | 2022-05-16 | Rework | Operator | 17714-1 |  | Scratched up parts. Ahmed stacked these very close to the edge of the table. They were knocked down and ~20 had to sanded and repainted | Assembly | Assembly | Ahmed | Be mindful of where the parts are stored | Prevent tipping/ tripping hazards
27 | 2022-05-17 | Rework | Paint - Prep | 17705-11 |  | Every one of the floor stands had grit on the inside. Parts were not washed properly | Paint | Paint |  | Check and flag parts that are not ok to process | Sand and paint green all 26 parts
28 | 2022-05-17 | Scrap | Supplier | 17642-1 |  | Vendor cut insulation out of thicker insulation. Vendor cut insulation out of thicker material which causes interference | Assembly | Supplier |  |  | Have vendor recut part
29 | 2022-06-01 | Scrap | Operator | 17655-2 |  | Formed incorrectly. Assumed part was symmetrical | Welding | Brake | Brian | Check drawing properly | Fix drawing
30 | 2022-06-02 | Scrap | Operator | 17655-2 |  | Formed incorrectly. Didnt identify the flat properly | Welding | Brake | Brian | Check drawing properly | Added dimensions to make it clear
31 | 2022-06-02 | Scrap | Operator | 17697-1 |  | Formed incorrectly. Realized after anodizing that the uprights were incorrectly formed | Assembly | Brake | Brian | First off inspection | Recut parts
32 | 2022-06-02 | Rework | Operator | 17705-6 |  | Parts were sent without HDG. Closed WO without making sure that all the sequences were complete | Customer | Shipping |  | Read WO | Ensure all seq are signed before closing
33 | 2022-06-02 | Scrap | Operator | 17705-6 |  | Parts were not to spec. The programmed parts had the wrong compensation (oxygen instead of nitrogen). Merryl didnt do the first off inspection and customer got the wrong part | Customer | Programming | Merryl/ Syed | Check program | Ensure first part is to spec
34 | 2022-06-03 | Rework | Operator | 17764-4 |  | Incorrect jig. Jig was flipped incorrectly and hole was drilled on the wrong side of the bottom. Recut jig correctly and used slugs from the right hole to fill wrong hole | Welding | Engineering | Jonas | Check jig against model | Recut jig and mirroed it, and Blake reworked the parts
35 | 2022-06-03 | Scrap | Operator | 17697-1 |  | 2 uprights not to spec. Brian did not use die liners and the parts had brake lines. Cant be sent for anodizing | Brake | Brake | Brian | Ensure everything is in order before forming | Recut parts
36 | 2022-08-29 | Scrap | Operator | 17824-1 |  | Bottom formed inside out. Drawing didnt identify, part looked symmetric. | Weld | Engineering
37 | 2022-08-29 | Scrap | Operator | 17824-1 |  | Backpans not correct. Backpans were short, had to recut and rush them out | Customer | Engineering
38 | 2022-08-29 | Rework | Operator | 17824-1 |  | Doors did not align properly. hinges were welded in the wrong spot which cause the doors to be 3/16 out | Weld | Engineering |  | Need to make jigs
39 | 2022-08-29 | Rework | Engineering | 17813-1 |  | Finish was supposed to be 2B not #4. Miscommunication resulted in using #4 material instead of 2B | Weld | Engineering |  | Pad sand all 11 units
40 | 2022-08-30 | Rework | Operator | 17813-1 |  | Spot welds need to be ground down. Grind all the plug welds down and pad sand again | Assembly | Engineering |  | Remodel how to weld the internals properly
41 | 2022-08-26 | Deviation | Engineering |  |  | Doors dont sit properly, they shift up when locked. Need to get latch support for the door to make it sit flush | Assembly | Engineering
42 | 2022-08-26 | Deviation | Operator |  |  | Warpage on the bottom. Can rock the unit back and forth. Too hot? | Assembly | Welding
43 | 2022-08-26 | Rework | Engineering |  |  | Holes are too small on the unit to get the mounting panel on . Ream holes to be bigger | Assembly | Engineering
44 | 2022-08-30 | Rework | Time | 17746-2 |  | B.O.M. & Routing issues. Routings not accurate - missing parts etc. - see work order for Redlined notes | Scheduling | Engineering | Junfeng
45 | 2022-08-31 | Rework | Routing | 17827-1 |  | Missing brackets & hinge & rod on Routing. Routings not accurate - missing parts etc. - see work order for Redlined notes | Assembly | Engineering | Junfeng
46 | 2022-08-31 | Rework | Operator | 17848-1 |  | Missing parts . Quantity was not checked by operator - missed cutting offcut program | Brake | Laser | Florin | Cut all programs released | Count parts after completion
47 | 2022-09-01 | Rework | Operator | 17846-1 |  | Brkts not formed. Work order filled up but missed the brackets | Welding | Brake | Brain | check routing | ensure all parts for order are formed
48 | 2022-09-12 | Rework | Engineering | 17746-4 |  | Missing cutouts for flanges on the bottom. Bottom panel needs 4 flanges, only has cutouts for 2 | Brake | Engineering |  | Check drawing before release | Need to recut parts on laser
49 | 2022-09-12 | Rework | Operator |  |  | Missing parts such as perf and others. | Brake | Laser
50 | 2022-09-12 | Rework | Operator | 17881-2 |  | Burr left on parts. Parts are being being sanded or deburred properly | Brake | Punch | Hao | Follow through on responsibilites | Already talked about it twice last week, will have a chat expaining WO time and help seq
51 | 2022-09-12 | Rework | Programming | 17876-5 |  | Knockouts punched wrong way. Oversight while programming Knockouts - missed reading Form down note | NC | Programming | Syed | Read all notes on drawing | Fixed program for next run
52 | 2022-09-13 | Rework | Operator | 17846-1 |  | Pad sanded 304 # 4 gland plates for the Enclosure. Drawing was not read prior to Assembly | Assembly | Assembly | Eddie | Read drawings
53 | 2022-09-15 | Rework | Operator | 17888-1 |  | Square hole punched instead of Round hole. Setup error and not checked first off | Brake | Punch | Hao/Florin | Double check setup & check first off | Reminded operators to check first off
54 | 2022-09-19 | Rework | Operator | Multiple |  | Overwriting PS. |  | Shipping
55 |  | Rework | Shipped Incomplete |  |  | Shipped parts without assembly. |  | Shipping
56 | 2022-09-21 | Rework | Operator | 17853-2 |  | Formed inside out. |  | Brake
57 | 2022-09-21 | Scrap | Operator |  |  | Light Paint. |  | Paint
58 | 2023-01-31 | Rework | Programming | 18107-1 |  | Missing obround on part after it was cut. Dxf file obround was pulled into Cypcut as a block and was deleted and programmed as is, first off was not checked by operator either | Laser | Laser | Syed/Florin | Double check dxf file for blocks and check first off | Fixed the dxf file and reminded operator to ceck first off
59 | 2023-03-08 | Scrap | Operator | 18121-1 |  | Flange was formed 0.5" instead of 0.38". Holes deformed and unacceptable for type 4. Drawing was read incorrectly. In addition, the assembly has 2 variations of stiffener flages, 0.5" and 0.375" | Assembly | Brake | Brian | Recut and reform x4 0000-8047 bodies | Standardize flange size, first off inspection and read drawings
60 | 2023-03-09 | Rework | Operator | 18154-1 |  | Frames was welded incorrectly. Some frames had hinge holes on both arms and others none. Craig was on auto pilot and used 2 of the hinge hole arms on the same frame | Engineering | Weld | Craig |  | First off inspection and check drawing
61 | 2023-03-08 | Rework | Tooling | 18057-2 |  | Pem tool left indentations on the door, need to buff . Didnt notice the indentiations thet pem tools leaving indentations | Welding | Pem | TJ |  | Pem tools in question were sahved flat using the Togu
62 | 2023-03-13 | Scrap | Operator | 18168-1 |  | Bodies were formed along the wrong edge. Brain read the drawing wrong and formed the part using the wrong edge | Brake | Brake | Brian |  | Check drawings and first part before going through the order
63 | 2023-03-16 | Rework | Operator | 18108-1 |  | Scratches on #4 SST. Scratches due to material handling. Sometimes covered by SPV so we dont see until we peel it off the part | Assembly |  |  |  | Proper material handling, use cardboard/ paper between parts. Filled the scratch and polished it to finish
64 | 2023-03-16 | Deviation | Tooling | 18121-1 |  | Arc out during stud welding caused imperfection on the unit. Copper slat might have had an imperfection which caused on arc out | Welding | Weld | Craig | Craig proactively cleaned up the copper slates | Arc out by the glad plate so dustin okayed it
65 | 2023-03-17 | Rework | Extra Parts | 19890-1 |  | More of one and less of the other. | Brake | Laser
66 | 2023-03-21 | Deviation | Extra Parts | 18176-4 |  | Extra 47 pcs. Count was incorrect | Timesave | Laser | Florin
67 | 2023-03-22 | Rework | Operator |  |  | Encl doors had paint hook marks . Incorrect hooks used to suspend doors in paintline | Customer | Paint |  |  | Use the curved/ kinked hooks to suspend doors for paint
68 | 2023-03-24 | Rework | Paint - Prep | 19887-1 |  | Paint issues. | Paint | Paint |  | Repaint | Grit issues
69 | 2023-04-05 | Rework | Operator | 18129-2 |  | Doors had brake line marks. Brain assumed that SPV will protect against brake line marks, he didnt use neoprene | Assembly | Brake | Brian | Regrain doors | Peel back SPV after first part and use neoprene if needed
70 | 2023-04-10 | Rework | Engineering |  |  | Holes too small for M3, M5 pem nuts were swapped for 10-32, warping and some staining issues. WIP | Customer | Production
71 | 2023-04-11 | Scrap | Engineering | 18132-1 |  | Top and bottom was swapped during welding. Top and bottom was swapped, body was painted and assembled. Balwinder found issue when testing | Engineering | Welding | Blake |  | Ensure that items are made per drawing
72 | 2023-04-11 | Rework | Operator | 18132-3 |  | Welds broke when trying to fix warpage. Unit was warped due to heat from welding, Lance attempted to fix the warpage. Warpage was fixed at the cost of the welds breaking | Assembly | Assembly/ Welding | Lance/ Joe |  | Try to dissipate heat better/ not put as much heat
73 | 2023-04-11 | Rework | Operator | 18142-2 |  | Paint looks dry, has enough coverage. Had issues recoating the unit | Paint | Paint | Suagam |  | Do it once and do it right
74 | 2023-04-11 | Deviation | Operator | 18155-1 |  | Too much stud weld heat caused minor warpage on the doors of the unit. | Assembly | Welding
75 | 2023-04-15 | Deviation | Programming | 18206-4 |  | Cut 2 extra, WO didnt have correct qty. Same issue, Hao cut extra when he didnt have to. He did not have the correct qty on the WO | Lead | Punch | Hao |  | Read the WO qty, count the parts and have the correct qty on the WO
76 | 2023-04-17 | Scrap | Operator | 18189-10 |  | Bottom door flange and door lip were formed to the wrong dimensions. Programmed the door wrong on the brake. Door lip and bottom flange dimensions were swapped | Brake | Brake | Brian | Brain said he did the first off inspection but didnt catch the error | Read the drawing, and first off inspection
77 | 2023-04-19 | Scrap | Extra Parts | 18236-1 |  | 96 extra cut (20 thou short). No first off inspection. Cut 96 extra pieces which are out of tolerance, WO qty was not correct | Lead | Punch | Hao
78 | 2023-04-17 | Rework | Operator | 18189-10 |  | Body moved when forming the left side (when measured, top was 0.0625" bigger than bottom). Body was not aligned with the stoppers when the side was formed. Mike had a TJ helping him with when forming bodies | Assembly | Brake | Mike | As the helper is inexperienced , make sure that he is aware of correct positioning | Ensure that body is against the brake stoppers
79 | 2023-05-01 | Scrap | Operator | 18233-1 |  | New part, 2pcs were not formed to the drawing. Part wasnt formed to drawing specs | Brake | Brake | Brian
80 | 2023-04-23 | Rework | Paint - Prep |  |  | Paint blemishes. Blemishes on 3 bodies should have been caught in production before shipping it to customer | Customer | Paint |  | Had a talk with assembly | Parts must be QC'd before going off to the next station/ customer
81 | 2023-05-01 | Rework | Operator | 19894-1, 18100-2 |  | Pems were installed to the wrong side. Drawing was ready incorrectly | Welding | Misc | TJ |  | First off inspection and check drawing
82 | 2023-12-05 | Scrap | Operator |  |  | edge bent while on pallet as received . Not aligned on the pallet, edge hung over and was bent | Brake | Brake |  | recut and reform x1 body | make sure the material is centred and the egdes of the piece are supported.
83 | 2023-12-05 | Rework | Operator | 18591-1 |  | did not cut down gasket, used full size 3/8" X1" instead of cutting down to 5/8"X1", hinge on backwards. Drawing was not clear as to the orientation of the hinge knukle, instructions were poor on gasket cutting. | Assembly | Assembly/Welding | Saurobh | Gasket removed/redone and hinge drilled and refastened | Read the drawing, and first off inspection
84 | 2023-12-06 | Rework | Operator | 18591-1 |  | Gasket cut to 5/8 uneven some problem rivets. improper cut, knife needs to be sharp and placement needs to be straight | Assembly | assembly/Welding | Saurobh |  | attention to detail, using a ruler and place jagged sides facing into the corner, rivet gun needs to be turned up.
85 | 2023-12-06 | Rework | Surface Imperfection | 18590-1 |  | break marks on finished painted enclosure, jagged on the inside edge, safety issue, some paint drips. Brake leaving marks on formed pieces | Paint | Brake | brian |  | use neoprine or coated aluminium, sanding part to decrease jagged surface.
86 | 2023-12-07 | Rework | Paint - Prep | 18591-1 |  | paint contamination, two areas with dust bumps. dirt from the line fell onto the piece | Assembly | Paint |  |  | in the morning clean the rail to remove the dust.
87 | 2023-12-08 | Rework | Paint - Prep | 18561-1 |  | Paint contamination on top of box . incomplete wash procedure left residue on the enclosure surface. Not caught before assembly. | Assembly | Paint |  |  | spoke with Dan agreed that going forward we need to be extra vigilant on the final rinse to make sure item is clean
88 | 2023-12-11 | Rework | Paint - Prep | 18570-1 |  | Paint layer issue. dust contamination | Assembly | paint |  |  | Spoke with Dan going forward we need to minimize dust, cleaning the rail to make sure dust is at a minimum
89 | 2023-12-12 | Rework | Operator | 18577-3 |  | the slot was a hole and not fully open on the end. parts were from an old revision , left over taken from the shelf | Assembly
90 | 2023-12-12 | Rework | Operator | 18577-3 |  | the end piece that would go into the slot had a notch in it. . parts were from an old revision , left over taken from the shelf | Assembly
91 | 2023-12-29 | Rework | Operator | 18479-10 |  | security screw hole too large, wrong place. | Assembly | assembly
92 | 2023-12-29 | Rework | Operator | 18479-12 |  | security screw hole too large, wrong place, hings welded out on alignment. | Assembly | Welding | blake
93 | 2023-12-29 | Scrap | Engineering | 18599-1 |  | window opening too large for window provided, wrong revision. . door skin used wrong revision, Door drawing 0000-7407 has been updated to Rev 02. | Assembly | engineering | junfeng
94 | 2023-12-29 | Rework | Operator | 18574-1 |  | camera space, impeded upon by weld and box uniformity. the opening should have been laser cut, box formed with seam on rear | Assembly | engineering | jonas | filed camera opening, touched up paint. | drawing wo redesign
95 | 2023-12-29 | Rework | Operator | 18574-1 |  | paint thin needs repaint. more paint needed | Assembly | Paint |  | repaint | check depth of paint with meter and light
96 | 2023-12-29 | Rework | Operator | 18587-1 |  | Hinge clearance issue, paint removed from hinge when door opened. jig and welder inexperience | Assembly | welding | Ramon | hinge bent out and repainted. | further training, looking at standardized jigs
97 | 2024-01-08 | Rework | Operator | 18600-1 |  | Stud weld stripped when putting insulation bracket on. possible over tightening | Assembly | assembly | lance | 20 minutes cut off and restud
98 | 2024-01-08 | Rework | Operator | 18589-1 |  | side frame hole do not line up. the pem was placed into the socket with too much pressure warping the frame | Assembly | Laser |  | disassemble, recut new frames on laser, weld and assemble frames | a lower pem pressure eliminates the warp caused by over stressing the material
99 | 2024-01-18 | Rework | Surface Imperfection | 18625-1 |  | grind marks, high gloss paint shows . over ground by Dan and Randy | Assembly | Paint
100 | 2024-01-18 | Rework | Operator | 18616-1 |  | welds too large, . too much weld, | Paint | welding | craig | cap grind weld, weld ground smoth on front per jonas
101 | 2024-01-19 | Rework | Surface Imperfection | 18495-5 |  | grind marks, high gloss paint shows . over ground unknown worker | Assembly |  |  |  | showing the teams the marks and teling them how to avoid making these
102 | 2024-01-19 | Rework | Paint - Prep | 18495-3 |  | bad paint finish. contaminant | Assembly | Paint |  | paint was informed | extra vigilant on cleaning the rails
103 | 2024-01-23 | Rework | Operator | 18514-4 |  | hinge too long creating a zone that does not have clearance . hinge should have been cut shorter before installation. | Assembly | assembly | Saurobh | Gasket removed/redone and hinge cut and refastened | will speak to the night shift about hinge clearance.
104 | 2024-01-27 | Rework | Engineering | 18606-1 |  | inside plate was installed backwards, . poor drawing, hard to spot even when pointed out by customer | Customer | assembly |  | Drill a half inch hole on correct side for wiring. disassembly need to occur on 9 units. | detail needed on drawing specific to orientation
105 | 2024-01-29 | Rework | Operator | 18625-1 |  | tap broke off in enclosed pem. tap pushed into the end of the enclosed pem, snapped tap off in pem | Assembly | assembly | eddie |  | dont bottom out the pem
106 | 2024-02-01 | Rework | Operator | 18663-1 |  | pem process left marks and dents in #4 finish. wrong pressure/ uneven part during pem process left marks and dents | Assembly | assembly | joe |  | check sequence for pem pressure and pem platform size.
107 | 2024-02-12 | Scrap | Operator | 18644-3 |  | bracket formed uneven, cannot use due to tight tolerances. | Assembly | Brake
108 | 2024-02-13 | Rework | Shipped Incomplete | Rittal |  | missing hardware. forgot to send hardware for the 2 tophats | Customer | assembly
109 | 2024-02-14 | Scrap | Programming | 18566-3 |  | wrong door kit 2804. wrong door kit | welding | Programming |  |  | double check drawing
110 |  | Rework | Operator | 18536-3 |  | scratches on 2 doors. poor material handling | Assembly |  |  | buffed and sanded out | be careful of the surface
111 |  | Rework | Operator | 18559-4 |  | exterior has ts marks, poor pad sanding. TS leaving pad marks , hard to sand off | Assembly | assembly
112 | 2024-01-03 | Rework | Operator | 18566-4 |  | back side of panel deep line. |  | Weld | Craig | weld and grind smooth
113 | 2024-01-23 | Scrap | Engineering | 18616-1 |  | part formed and pemmed backwards. Drawing had a subtle difference in hole orientation, pemming a flat piece, very hard to see | Assembly | assembly | eddie | team made aware of the issue of studying the drawing | make a note on the drawing for caution about which side to pem, proper orientation.
114 |  | Rework | Engineering | 18614-3 |  | part formed out. prototype issues | Assembly | Engineering
115 | 2024-02-21 | Rework | Operator | 18659-1 |  | missing pem in box. missed, human error | Paint | assembly |  | box deconstructed,pemmed then reweld and paint | be more vigalent
116 | 2024-02-23 | Scrap | Operator | 18671-1 |  | part formed backwards. missed, human error | Assembly | Brake | Brian | First off to be conducted by Plant manager | vigilant on the first off
117 | 2024-02-23 | Rework | Operator | 18696-1 |  | paint issue. gun release splatter/ over charging. repaint needed time for the part to disapate the electric charge | Assembly | Paint | dan |  | wash the part or wait a longer period of time
118 | 2024-02-23 | Scrap | Operator | 18681-1 |  | part hanging over the edge of the pallet on the floor was bent. part was hanging out over the edge of the pallet and was stepped on/hit |  |  |  | new part being cut | parts need to be flush to pallet edge and not stored on the floor
119 | 2024-02-26 | Scrap | Operator | 18650-1 |  | part formed backwards. drawing of part upper right, showed part but the bracket was not shown with a dotted line | welding | Brake |  | new part being cut and formed | Dotted line showing items on the backside
120 | 2024-03-05 | Rework | Operator | 18644-3 |  | paint issue on lower half of cart, missed areas, over charging. | Assembly | Paint
121 | 2024-03-05 | Rework | Operator | 18644-3 |  | door tabs not ground off. . | Assembly | Welding
122 | 2024-03-06 | Rework | Operator | 18644-3 |  | doors not fitting. doors and bodies were number matched, in the welding process the number on the body was covered by the flange. | Assembly | Welding |  |  | future orders with have the door more heavily stamped and the stamp on the body with be centre top
123 | 2024-03-14 | Rework | Operator | 18638-1 |  | electrocleaning solution not properly taken off welds, stain left behind. the acid was not properly neutralized which lefd a stain on the product | Assembly | assembly | surrobh | rewash and reneutralize | retraining of the new procedures to ensure proper removal of the acid
124 | 2024-03-14 | Rework | Operator | 18644-3 |  | bar width too wide for alllocated space. set up for weld was out by 1/16 to 1/8th | Assembly | Welding | ian | craig trimmed of the space to allow fitment | more vigilance when welding, use a jig for accuracy
125 | 2024-03-15 | Rework | Operator | 18655-9 |  | back weld seem too large to accomodate the gasket to be fitted. forgot to grind down the weld, confused with spec from previous subcoe | Paint | welding | joseph | ground down the welds to acceptable level | ask
126 | 2024-03-25 | Rework | Paint - Prep | 18697-1 |  | prairie white has grit in the finish. problem with paint, seems to be prone to grit in finish | Assembly | paint |  | sand, wash and repaint. | change paint
127 | 2024-03-25 | Rework | Paint - Prep | 18697-1 |  | box has grit and the edge needs to be deburred. more sanding needed and priarie white problems | Assembly | Paint |  | sand, wash and repaint. | change paint
128 | 2024-03-26 | Rework | Surface Imperfection | 18652-4 |  | pem process left marks and dents in #4 finish. pem machine base and top strut are worn causing movement, aso micro debris around pem hole | Assembly |  |  | clean, buff, hand polish to regrain | make sure dies are clean and surface is free from debris.
129 | 2024-04-24 | Rework | Surface Imperfection | 18632-3 |  | scratches and heavey brake marks in surface. handling, over pressure. | welding | Brake | mike
130 | 2024-04-25 | Scrap | Operator | 18680-2 |  | 1 piece mis formed. | brake | Brake | brian
131 | 2024-04-25 | Rework | Operator | 18713-1 |  | weld bumps in surface from burn through. too hot on sst, laser weld recomended | Assembly | Welding | craig |  | laser weld or weld studd